## Project Management Plan
Week | Tasks | Effort (days)
2022-01-01 | Brainstorm inital concept | 2
2022-01-08 | Decide on tech stack | 1
2022-01-15 | Decide on service providers | 3
2022-01-22 | Meet with stakeholders | N/A
2022-01-29 | Acquire or allocate dev talent | 4
2022-02-05 | Plan development budget | 2
2022-02-12 | Meet with stakeholders | 3
2022-02-19 | Create UI/UX mockups | 4
2022-02-26 | Create App Architecture Outline | 2
2022-03-05 | Create process diagrams | 3
2022-03-12 | Meet with stakeholders | N/A
Q1 Goal
Complete Proof of Concept
Week | Tasks | Effort (days)
2022-03-12 | Create inital UI | 2
2022-03-19 | Create automated UI tests | 2
2022-03-26 | Deliver UI to backend developers | 1
2022-04-02 | Finalize proof of concept | 2
2022-04-09 | Test first API endpoint (ping) | 1
2022-04-16 | Create inital dummy data responses | 2
2022-04-23 | Complete inital backend development | 3
2022-04-30 | Create build system | 4
2022-05-07 | Test continuous delivery | 2
2022-05-14 | Provision Build Server | 2
2022-05-21 | Finish inital DevOps | 1
2022-05-28 | VACTION!!
Q2 Goal
Complete DevOps
Week | Tasks | Effort (days)
2022-06-04 | Deploy to Dev! | 2
2022-06-11 | Complete Initial API development | 1
2022-06-18 | Conduct End User Testing | 3
2022-06-25 | Gather feedback results | 2
2022-07-02 | Create outline for desired changes | 4
2022-07-09 | Meet with stakeholders | 2
2022-07-16 | Make any necessary changes | 3
2022-07-23 | Finalize changes in roadmap | 4
2022-07-30 | Develop enhancement requests | 2
2022-08-06 | Integrate changes | 1
2022-08-13 | Update product roadmap | 1
2022-08-20 | Meet with stakeholders | N/A
2022-08-27 | Go live! | N/A
Q3 Goal
Complete Development
Week | Tasks | Effort (days)
2022-09-03 | Demo finished product | 2
2022-09-10 | Gather Release Notes | 1
2022-09-17 | Edit Release Notes | 3
2022-09-24 | Meet with stakeholders | N/A
2022-10-01 | Create Initial Outline for Documentation | 2
2022-10-08 | Finish Outline for Documentation | 2
2022-10-15 | Create REAME.md (Getting Started) | 3
2022-10-22 | Create Support/Help Guide | 4
2022-10-29 | Create API Developer Guide | 2
2022-11-05 | Create API User Manual | 4
2022-11-12 | Meet with stakeholders | N/A
2022-11-19 | Publish Documentation | 1
2022-11-26 | Finish Documentation | 1
Q4 Goal
Complete Documenation